## Sheet1
User Stories:
Story ID | User Story | Priority | Story Points
US-001 | As a student, I want to register an account so that I can access placement opportunities. | High | 5
US-002 | As a user, I want to log in securely so that I can access my dashboard. | High | 3
US-003 | As a user, I want to log out of the system so that my account remains secure. | Medium | 2
US-004 | As a user, I want role-based access so that I only see features relevant to me. | High | 5
Tasks:
Task ID | Task | Owner
PM-01 | Configure Jira Scrum Project | Project Manager
PM-02 | Create Sprint 1 Board | Project Manager
PM-03 | Conduct Sprint Planning Meeting | Project Manager
PM-04 | Assign Sprint Tasks | Project Manager
PM-05 | Prepare Weekly Status Report | Project Manager
Frontend Tasks:
Task ID | Task | Owner
FE-01 | Design Registration Page UI | Frontend Developer 1
FE-02 | Design Login Page UI | Frontend Developer 2
FE-03 | Implement Registration Form Validation | Frontend Developer 1
FE-04 | Implement Login Form Validation | Frontend Developer 2
FE-05 | Create Logout Functionality UI | Frontend Developer 1
Backend Tasks:
Task ID | Task | Owner
BE-01 | Create User Database Schema | Backend Developer 1
BE-02 | Develop Registration API | Backend Developer 1
BE-03 | Develop Login API | Backend Developer 2
BE-04 | Implement Password Hashing | Backend Developer 2
BE-05 | Implement Role-Based Access Logic | Backend Developer 1
BE-06 | Create Logout Session Handling | Backend Developer 2
QA Tasks:
Task ID | Task | Owner
QA-01 | Prepare Authentication Test Cases | QA Tester
QA-02 | Execute Registration Testing | QA Tester
QA-03 | Execute Login Testing | QA Tester
QA-04 | Execute Role-Based Access Testing | QA Tester
QA-05 | Log and Track Defects | QA Tester
Sprint Risks:
Risk ID | Risk | Impact | Mitigation
RSK-01 | Requirement misunderstanding | Medium | Clarify requirements during daily discussions
RSK-02 | Backend implementation delay | High | Prioritize API development early
RSK-03 | Authentication defects | Medium | Early QA involvement
RSK-04 | Integration issues | Medium | Perform incremental testing