## Sheet1
Risk ID | Risk Description | Category | Probability | Impact | Risk Owner | Mitigation Strategy | Contingency Plan | Status
RSK-01 | Project requirements may change during development. | Scope | High | Medium | Project Manager | Conduct weekly requirement reviews and obtain approval before changes. | Move new requirements to future sprint or release. | Open
RSK-02 | Backend development tasks may take longer than estimated. | Schedule | Medium | High | Backend Developer | Prioritize critical APIs and monitor progress weekly. | Reallocate tasks or reduce lower-priority scope. | Open
RSK-03 | Integration issues between frontend and backend modules. | Technical | Medium | High | Development Team | Perform early integration testing and regular code reviews. | Allocate additional testing time. | Open
RSK-04 | Testing activities may be delayed due to incomplete features. | Quality | Medium | Medium | QA Tester | Involve QA early in development and testing preparation. | Extend testing effort within sprint buffer time. | Open
RSK-05 | Scope creep caused by additional feature requests. | Scope | High | High | Project Manager | Follow formal change request process. | Defer requests to future releases. | Open
RSK-06 | Team members may have academic workload conflicts during project execution. | Resource | Medium | Medium | Project Manager | Plan work in advance and monitor task completion. | Redistribute workload among team members. | Open
RSK-07 | Database design issues may affect application performance. | Technical | Low | High | Backend Developer | Review database design before implementation. | Refactor database structure if required. | Open
RSK-08 | Defects discovered late in the project may delay release. | Quality | Medium | High | QA Tester | Conduct testing throughout each sprint.