## Sheet1
Team Member:
Team Member | Role
Karthick Raja | Project Manager
Ganesh Kumar | Frontend Developer
Saravanan M | Frontend Developer
Vignesh S | Backend Developer
Naveen Kumar | Backend Developer
Hari Prasad | QA Tester
RACI Legend:
Symbol | Meaning
R | Responsible (Performs the work)
A | Accountable (Owns the outcome)
C | Consulted (Provides input and feedback)
I | Informed (Kept updated on progress)
Responsibility Assignment Matrix:
Activity | PM | FE-1 | FE-2 | BE-1 | BE-2 | QA
Project Charter Creation | A/R | I | I | I | I | I
Stakeholder Analysis | A/R | I | I | I | I | I
Requirements Gathering | A | C | C | C | C | I
Scope Definition | A/R | I | I | I | I | I
Product Backlog Creation | A/R | C | C | C | C | I
Sprint Planning | A | C | C | C | C | C
Jira Board Management | A/R | I | I | I | I | I
UI Design | I | A/R | R | I | I | I
Frontend Development | I | A/R | R | I | I | I
Backend Development | I | I | I | A/R | R | I
Database Design | C | I | I | A | R | I
API Development | I | I | I | A/R | R | I
Integration Activities | C | R | R | R | R | I
Unit Testing | I | R | R | R | R | C
Integration Testing | I | C | C | C | C | A/R
User Acceptance Testing | C | I | I | I | I | A/R
Bug Tracking | C | R | R | R | R | A
Risk Management | A/R | I | I | I | I | I
Change Request Evaluation | A/R | C | C | C | C | I
Weekly Status Reporting | A/R | I | I | I | I | I
Sprint Review Meeting | A | C | C | C | C | C
Sprint Retrospective | A | C | C | C | C | C
Release Preparation | A | C | C | C | C | R
Project Closure Report | A/R | I | I | I | I | I
Final Project Presentation | A/R | C | C | C | C | C