## Sheet1
Risk ID | Risk Description | Category | Probability | Impact | Mitigation Strategy | Current Status
RSK-01 | Project requirements may change during development | Scope | High | Medium | Weekly stakeholder reviews and backlog refinement | Monitoring
RSK-02 | Backend development tasks may exceed estimates | Schedule | Medium | High | Sprint tracking and workload balancing | Monitoring
RSK-03 | Frontend and backend integration issues | Technical | Medium | High | Early integration testing and code reviews | Mitigated
RSK-04 | Testing activities delayed due to incomplete features | Quality | Medium | Medium | Early QA involvement in each sprint | Mitigated
RSK-05 | Scope creep from additional feature requests | Scope | High | High | Formal change request process | Monitoring
RSK-06 | Team academic workload affecting availability | Resource | Medium | Medium | Advance sprint planning and workload adjustment | Monitoring
RSK-07 | Database design issues affecting performance | Technical | Low | High | Database review and optimization testing | Closed
RSK-08 | Defects discovered late in development cycle | Quality | Medium | High | Continuous testing throughout sprints | Monitoring
RSK-09 | Recruiter Portal workflow complexity higher than estimated | Technical | Medium | Medium | Additional QA sessions and integration testing | Monitoring
Probability:
Rating | Description
Low | Unlikely to occur
Medium | May occur during project
High | Likely to occur during project
Impact:
Rating | Description
Low | Minor effect on project
Medium | Moderate impact on project
High | Significant impact on schedule, scope, or quality