## Sheet1
Stakeholder ID | Stakeholder | Role | Interest Level | Influence Level | Expectations | Communication Method | Communication Frequency
ST-01 | Students | Primary End Users | High | Medium | Easy access to job opportunities, application tracking, and placement updates | Email, Project Demonstrations | Bi-Weekly
ST-02 | Placement Officer | Project Sponsor / System Administrator | High | High | Centralized management of placement activities and reporting capabilities | Meetings, Status Reports | Weekly
ST-03 | Recruiters | External Users | Medium | High | Ability to post jobs, review applicants, and shortlist candidates efficiently | Email, Demonstrations | Monthly
ST-04 | Development Team | Project Execution Team | High | Medium | Clear requirements, timely feedback, and effective project coordination | Scrum Meetings, Jira Updates | Weekly
ST-05 | QA Tester | Quality Assurance | High | Medium | Stable builds and clear acceptance criteria for testing activities | Sprint Reviews, Meetings | Weekly
ST-06 | Faculty Mentor | Academic Reviewer | Medium | Medium | Successful completion of project objectives and proper documentation | Progress Meetings | Monthly
ST-07 | College Management (Simulated) | Business Stakeholder | Medium | Low | Improved placement process and visibility into placement performance | Summary Reports | Monthly
Power–Interest:
Category | Stakeholders
Manage Closely | Placement Officer
Keep Satisfied | Recruiters
Keep Informed | Students
Monitor | Faculty Mentor
Team Structure:
Team Member | Role
Karthick Raja | Project Manager
Ganesh Kumar | Frontend Developer
Saravanan M | Frontend Developer
Vignesh S | Backend Developer
Naveen Kumar | Backend Developer
Hari Prasad | QA Tester