Additional Change Requests Report – Sprint 5

Project Name:

Sprint: Sprint 5

Reporting Period: Week 10

Document Version: 1.0

Purpose

Following the completion of the Placement Dashboard MVP, stakeholders reviewed the system and proposed additional enhancements.

The purpose of this document is to evaluate these requests through the project's formal change control process and determine whether they should be implemented before project closure.

Change Request Summary

| CR ID | Change Request | Requested By | Impact Level | Decision |
| --- | --- | --- | --- | --- |
| CR-07 | Department-Wise Placement Dashboard | Placement Officer | Medium | Approved |
| CR-08 | Placement Statistics PDF Export | Placement Officer | Medium | Approved |
| CR-09 | Email Notification System | Recruiter | High | Rejected |
| CR-10 | Interview Scheduling Module | Faculty Mentor | High | Deferred |

CR-07: Department-Wise Placement Dashboard

Request Information

Request ID: CR-07

Request Date: Week 10

Requested By: Placement Officer

Description

Display placement statistics separately for each academic department.

Examples:

- CSE Placement Rate

- ECE Placement Rate

- Mechanical Placement Rate

- Department-wise Application Counts

Business Justification

The Placement Cell frequently prepares department-specific reports for faculty and management review.

Impact Assessment

| Area | Assessment |
| --- | --- |
| Scope | Medium |
| Schedule | Low |
| Risk | Low |
| Development Effort | 4 Story Points |

Benefits

- Better placement analysis.

- Improved reporting visibility.

- Supports departmental review meetings.

Decision: Approved

Reason: The enhancement aligns with existing reporting functionality and can be completed during Sprint 6 without affecting project delivery.

Planned Implementation: Sprint 6

CR-08: Placement Statistics PDF Export

Request Information

Request ID: CR-08

Request Date: Week 10

Requested By: Placement Officer

Description

Allow placement statistics reports to be exported as PDF documents.

Business Justification

PDF reports are easier to share during meetings and maintain a consistent reporting format.

Impact Assessment

| Area | Assessment |
| --- | --- |
| Scope | Medium |
| Schedule | Low |
| Risk | Low |
| Development Effort | 3 Story Points |

Benefits

- Easier report distribution.

- Improved reporting professionalism.

- Supports project documentation requirements.

Decision: Approved

Reason: The request complements the Excel export functionality implemented in Sprint 5.

Planned Implementation: Sprint 6

CR-09: Email Notification System

Request Information

Request ID: CR-09

Request Date: Week 10

Requested By: Recruiter

Description

Automatically notify students when:

- Applications are shortlisted.

- Applications are rejected.

- New jobs are posted.

Business Justification

Would improve communication between recruiters and students.

Impact Assessment

| Area | Assessment |
| --- | --- |
| Scope | High |
| Schedule | High |
| Risk | Medium |
| Development Effort | 7 Story Points |

Risks

- Requires SMTP configuration.

- Additional testing effort.

- Potential deployment complexity.

Decision: Rejected

Reason: The functionality provides value but exceeds the remaining project capacity and introduces unnecessary deployment risk for the MVP release.

The feature is recommended for a future version.

CR-10: Interview Scheduling Module

Request Information

Request ID: CR-10

Request Date: Week 10

Requested By: Faculty Mentor

Description

Provide recruiters with the ability to:

- Schedule interviews.

- Allocate interview slots.

- Manage interview calendars.

Business Justification

Would improve recruitment workflow management.

Impact Assessment

| Area | Assessment |
| --- | --- |
| Scope | High |
| Schedule | High |
| Risk | High |
| Development Effort | 10 Story Points |

Risks

| Risk | Impact |
| --- | --- |
| Sprint 6 delay | High |
| Additional database redesign | High |
| Increased testing effort | High |
| Release schedule impact | High |

Decision: Deferred

Reason

The feature provides substantial value but exceeds MVP scope and cannot be completed without affecting the project closure timeline.

The request has been documented as a future enhancement.

Change Control Board Review

Participants

| Role | Representative |
| --- | --- |
| Project Manager | Karthick Raja |
| Frontend Team | Ganesh Kumar and Saravanan M |
| Backend Team | Vignesh and Naveen Kumar |
| QA Tester | Hari Prasad |
| Faculty Mentor | Kaaviya S |

Updated Change Request Statistics

| Metric | Value |
| --- | --- |
| Total Change Requests Submitted | 10 |
| Approved | 7 |
| Rejected | 2 |
| Deferred | 1 |
| Approval Rate | 70% |

Project Manager Analysis

The approved requests (CR-07 and CR-08) provide reporting enhancements while remaining within available Sprint 6 capacity.

The rejected and deferred requests would significantly expand project scope and create delivery risk. By documenting these requests and excluding them from the MVP release, the project maintains schedule commitments and scope integrity.

Lessons Learned

Positive Outcomes

- Stakeholder feedback was captured systematically.

- Scope decisions were supported by impact analysis.

- Approved enhancements aligned with business objectives.

Areas for Improvement

- Gather enhancement requirements earlier during planning.

- Conduct more frequent stakeholder demonstrations.

Conclusion

The Sprint 5 change review process ensured that valuable stakeholder enhancements were considered without compromising the project's delivery objectives.

Approved changes will be incorporated during Sprint 6, while larger requests have been documented for future releases. This approach supports controlled project growth and demonstrates effective project governance practices.