## Sheet1
Day | Date | Completed Work | In Progress | Blockers / Issues
Day 1 | Week 3 - Monday | Sprint Planning completed. Jira board configured. Sprint backlog finalized. | Registration page UI design. Database schema design. | None
Day 2 | Week 3 - Tuesday | Registration page wireframe completed. Users table created in MySQL. | Registration form development. Registration API development. | None
Day 3 | Week 3 - Wednesday | Registration form completed. Registration API developed. | Form validation and database integration. | Minor database connection issue identified.
Day 4 | Week 3 - Thursday | Database connection issue resolved. Registration module integrated successfully. | Login page UI development. Login API development. | None
Day 5 | Week 3 - Friday | Login page completed. Login API implemented. Authentication testing preparation started. | Login integration testing. Password hashing implementation. | None
Day 6 | Week 4 - Monday | Login integration completed. Password hashing implemented. | Logout functionality development. Test case creation. | None
Day 7 | Week 4 - Tuesday | Logout feature completed. Authentication test cases prepared. | Role-based access control implementation. | Access permission logic required additional clarification.
Day 8 | Week 4 - Wednesday | Role-based access logic completed. Student, Recruiter, and Placement Officer roles configured. | Functional testing of authentication module. | None
Day 9 | Week 4 - Thursday | Functional testing completed. Two defects identified and fixed. | Final regression testing. Sprint review preparation. | None
Day 10 | Week 4 - Friday | Regression testing completed. Sprint review demo prepared. Sprint documentation updated. | Sprint Review and Retrospective Meeting. | No major blockers.