Additional Change Requests Report

Project Name: Software Development Project Management Simulation: Campus Placement Portal

Sprint: Sprint 4

Reporting Period: Week 9

Purpose

This document records additional feature requests identified during Sprint 4 while demonstrating the project's change management process.

Each request was evaluated based on:

- Scope Impact

- Schedule Impact

- Risk Impact

- Development Effort

- Business Value

The purpose of the review was to ensure that only changes aligned with MVP objectives were approved.

Change Request Summary

| CR ID | Change Request | Requested By | Impact Level | Decision |
| --- | --- | --- | --- | --- |
| CR-05 | Dashboard Export to Excel | Placement Officer | Medium | Approved |
| CR-06 | Advanced KPI Analytics Widget | Faculty Mentor | High | Rejected |

CR-05: Dashboard Export to Excel

Request Details

Request ID: CR-05

Request Date: Week 9

Requested By: Placement Officer

Description

Placement officers requested the ability to export placement reports and dashboard data into Microsoft Excel format.

Examples:

- Applications Report

- Placement Statistics

- Hiring Funnel Data

Business Justification

Placement officers frequently prepare reports for:

- Faculty Review Meetings

- Department Reporting

- Accreditation Documentation

Exporting dashboard data would reduce manual effort and improve reporting efficiency.

Impact Assessment

| Area | Assessment |
| --- | --- |
| Scope | Medium |
| Schedule | Medium |
| Risk | Low |
| Development Effort | 5 Story Points |

Benefits

- Faster report generation.

- Improved stakeholder communication.

- Better data accessibility.

Risk Assessment

Potential Risks:

- Additional testing effort required.

- Data formatting inconsistencies.

Mitigation:

- Perform export validation testing.

- Use predefined report templates.

Decision: Approved

Reason for Approval:  The feature provides direct value to placement officers and supports reporting objectives already included in project scope.

Implementation Plan

Scheduled Sprint: Sprint 5

Priority: High

CR-06: Advanced KPI Analytics Widget

Request Details

Request ID: CR-06

Request Date: Week 9

Requested By: Faculty Mentor

Description

Add advanced analytics capabilities including:

- Department-wise placement forecasting

- Historical hiring trends

- Placement prediction charts

- Advanced performance metrics

Business Justification

Would provide additional analytical insights and enhance dashboard capabilities.

Impact Assessment

| Area | Assessment |
| --- | --- |
| Scope | High |
| Schedule | High |
| Risk | High |
| Development Effort | 8 Story Points |

Benefits

- Enhanced reporting capabilities.

- More detailed project analytics.

Risks Identified

| Risk | Impact |
| --- | --- |
| Sprint 5 schedule delay | High |
| Increased testing effort | Medium |
| Additional dashboard complexity | High |
| MVP release risk | High |

Schedule Impact Analysis

Current Sprint 5 Capacity: 24 Story Points

Additional Request: 8 Story Points

Potential Result:

- Reduced testing time

- Delayed dashboard delivery

- Increased project risk

Decision: Rejected

Reason for Rejection: The requested functionality exceeds MVP scope and would introduce significant schedule risk.

The feature may be considered in a future project phase after MVP completion.

Alternative Recommendation

Implement only basic dashboard metrics during Sprint 5 and document advanced analytics as a future enhancement.

Change Control Board Review

Participants

| Role | Representative |
| --- | --- |
| Project Manager | Karthick Raja |
| Frontend Team | Ganesh Kumar and Saravanan M |
| Backend Team | Vignesh S and Naveen Kumar |
| QA Team | Hari Prasad |
| Faculty Mentor | Kaaviya S |

Decision Criteria Used

The following criteria were used during evaluation:

| Criteria | Considered |
| --- | --- |
| Business Value | Yes |
| Scope Alignment | Yes |
| Schedule Impact | Yes |
| Resource Availability | Yes |
| Technical Risk | Yes |
| MVP Objectives | Yes |

Change Management Metrics

| Metric | Value |
| --- | --- |
| Total Change Requests Reviewed | 6 |
| Approved Requests | 5 |
| Rejected Requests | 1 |
| Approval Rate | 83.3% |
| Scope Creep Incidents | 0 |

Lessons Learned

Positive Outcomes

- Stakeholder requests were documented formally.

- Change requests were evaluated before implementation.

- Approved changes were integrated without affecting delivery commitments.

Improvement Opportunities

- Gather enhancement requests earlier during requirements workshops.

- Conduct stakeholder reviews before sprint planning.

Conclusion

The change management process successfully balanced stakeholder needs with project constraints. CR-05 was approved because it aligned with project reporting objectives and could be delivered within available sprint capacity. CR-06 was rejected to protect MVP scope, schedule, and release commitments.

The evaluation process helped maintain project scope integrity while ensuring valuable enhancements were considered through a structured governance approach.