## Change Request Summary
CR ID | Request Title | Requested By | Request Date | Impact Level | Effort (SP) | Decision | Implementation Sprint | Status
CR-01 | Job Search Filter | Student Users | Week 7 | Low | 3 | Approved | Sprint 3 | Implemented
CR-02 | Resume Download Option | Placement Officer | Week 8 | Medium | 5 | Approved | Sprint 4 | Implemented
CR-03 | Candidate Search Filter | Recruiter | Week 9 | Medium | 4 | Approved | Sprint 4 | Implemented
CR-04 | Company Profile Editing | Recruiter | Week 9 | Low | 2 | Approved | Sprint 4 | Implemented
CR-05 | Dashboard Export to Excel | Placement Officer | Week 9 | Medium | 5 | Approved | Sprint 5 | Implemented
CR-06 | Advanced KPI Analytics Widget | Faculty Mentor | Week 9 | High | 8 | Rejected | N/A | Closed
CR-07 | Department-Wise Placement Dashboard | Placement Officer | Week 10 | Medium | 4 | Approved | Sprint 6 | Planned
CR-08 | Placement Statistics PDF Export | Placement Officer | Week 10 | Medium | 3 | Approved | Sprint 6 | Planned
CR-09 | Email Notification System | Recruiter | Week 10 | High | 7 | Rejected | N/A | Closed
CR-10 | Interview Scheduling Module | Faculty Mentor | Week 10 | High | 10 | Deferred | Future Release | Deferred

## Change Request Details
Approved Requests
CR ID | Business Value | Impact on Scope | Impact on Schedule | Outcome
CR-01 | Improved job discovery | Low | None | Successfully Delivered
CR-02 | Easier resume access | Medium | Low | Successfully Delivered
CR-03 | Better candidate filtering | Medium | Low | Successfully Delivered
CR-04 | Improved recruiter experience | Low | None | Successfully Delivered
CR-05 | Enhanced reporting capability | Medium | Low | Successfully Delivered
CR-07 | Better departmental insights | Medium | Low | Planned
CR-08 | Improved report sharing | Medium | Low | Planned
Rejected Requests
CR ID | Reason for Rejection
CR-06 | Exceeded MVP scope and increased schedule risk
CR-09 | Additional infrastructure and testing effort required
Deferred Requests
CR ID | Reason for Deferral
CR-10 | Valuable feature but outside current MVP timeline

## Change Request Metrics
Request Statistics
Metric | Value
Total Requests Submitted | 10
Approved | 7
Rejected | 2
Deferred | 1

## Change Request Distribution
Category | Number of Requests
Student Features | 1
Recruiter Features | 3
Dashboard & Reporting | 4
Analytics Enhancements | 1
Communication Features | 1