## Defect Log
Campus Placement Portal – Defect Tracking Register
Defect ID | Sprint | Module | Defect Description | Severity | Status | Assigned To | Resolution Date
BUG-01 | Sprint 1 | Authentication | Login validation accepts empty username field | Medium | Closed | Backend Developer 1 | Week 4
BUG-02 | Sprint 1 | Authentication | Session not terminating after logout | Low | Closed | Backend Developer 2 | Week 4
BUG-03 | Sprint 2 | Resume Upload | Invalid file type accepted during upload | Medium | Closed | Backend Developer 2 | Week 6
BUG-04 | Sprint 2 | Student Profile | Form reset issue after profile update | Low | Closed | Frontend Developer 1 | Week 6
BUG-05 | Sprint 2 | Job Listings | Job listings sorting not working correctly | Low | Closed | Frontend Developer 2 | Week 6
BUG-06 | Sprint 3 | Job Application | Duplicate application submission allowed | Medium | Closed | Backend Developer 1 | Week 8
BUG-07 | Sprint 3 | Search Filter | Search results showing incorrect records | Medium | Closed | Backend Developer 2 | Week 8
BUG-08 | Sprint 3 | Application Tracking | Status display formatting issue | Low | Closed | Frontend Developer 2 | Week 8
BUG-09 | Sprint 4 | Job Posting | Form validation missing mandatory field check | Medium | Closed | Frontend Developer 1 | Week 9
BUG-10 | Sprint 4 | Candidate Search | Duplicate candidate results displayed | Medium | Closed | Backend Developer 1 | Week 9
BUG-11 | Sprint 4 | Shortlisting | Application status update delay | Low | Closed | Backend Developer 2 | Week 9
BUG-12 | Sprint 5 | Dashboard | Dashboard totals mismatch with database values | Medium | Closed | Backend Developer 1 | Week 10
BUG-13 | Sprint 5 | Reporting | Excel export formatting issue | Low | Closed | Frontend Developer 2 | Week 10
BUG-14 | Sprint 5 | Hiring Funnel | Funnel chart labels overlapping | Low | Closed | Frontend Developer 1 | Week 10
BUG-15 | Sprint 6 | PDF Export | Report generation failure for large datasets | Medium | Closed | Backend Developer 2 | Week 11
BUG-16 | Sprint 6 | Dashboard Analytics | Department statistics not refreshing correctly | Low | Closed | Backend Developer 1 | Week 11

## Defect Summary by Sprint
Sprint | Total Defects | Critical | Medium | Low | Closed | Open
Sprint 1 | 2 | 0 | 1 | 1 | 2 | 0
Sprint 2 | 3 | 0 | 1 | 2 | 3 | 0
Sprint 3 | 3 | 0 | 2 | 1 | 3 | 0
Sprint 4 | 3 | 0 | 2 | 1 | 3 | 0
Sprint 5 | 3 | 0 | 1 | 2 | 3 | 0
Sprint 6 | 2 | 0 | 1 | 1 | 2 | 0
Total Defect Summary
Severity | Count
Critical | 0
Medium | 8
Low | 8
Total | 16

## Defect Trend Analysis
Sprint | Defects Logged
Sprint 1 | 2
Sprint 2 | 3
Sprint 3 | 3
Sprint 4 | 3
Sprint 5 | 3
Sprint 6 | 2
Defect Distribution by Module
Module | Defect Count
Authentication | 2
Student Portal | 3
Job Applications | 3
Recruiter Portal | 3
Dashboard & Reporting | 5

## QA Metrics Dashboard
Key Quality Metrics
KPI | Target | Actual
Total Defects | < 20 | 16
Critical Defects | 0 | 0
Defect Closure Rate | > 95% | 100%
Open Defects Before Release | 0 | 0
Production Defects | 0 | 0