Velocity Tracking

PM Observations

Sprint 1

Observations

- Team onboarding period.

- Jira workflow setup.

- Initial Agile adoption.

Impact: Lower velocity due to setup activities.

Sprint 2

Observations

- Better requirement understanding.

- Improved team coordination.

Impact: Velocity increased to 20.

Sprint 3

Observations

- Application workflow development.

- Successful implementation of CR-01.

Impact: Velocity increased to 22.

Sprint 4

Observations

- Recruiter Portal completed.

- Multiple approved change requests implemented.

Impact: Highest productivity improvement.

Velocity reached 25.

Sprint 5

Observations

- Dashboard development required more complex reporting logic.

- The analytics module introduced additional testing effort.

Impact: Slight velocity decreases.

Velocity reduced to 24.

Sprint 6

Observations

- Stable development environment.

- Focused testing and deployment activities.

- Mature sprint planning process.

Impact: Velocity improved to 26.

KPI Summary

| KPI | Target | Actual |
| --- | --- | --- |
| Average Velocity | 20 | 22.5 |
| Final Velocity | 24+ | 26 |
| Sprint Completion Rate | 90% | 100% |
| Sprint Delivery Success | 90% | 100% |

Project Manager Conclusion

The project team demonstrated continuous improvement throughout the six sprint cycle. Velocity increased from 18 story points during Sprint 1 to 26 story points during Sprint 6, indicating improved team collaboration, better sprint estimation, and more effective Agile practices.

The velocity trend suggests that retrospective actions, backlog refinement sessions, and proactive risk management contributed positively to overall team performance.