## Velocity Summary
Campus Placement Portal – Sprint Velocity Tracking
Sprint | Duration | Planned Story Points | Completed Story Points | Velocity | Completion Rate
Sprint 1 | Week 3–4 | 18 | 18 | 18 | 100%
Sprint 2 | Week 5–6 | 20 | 20 | 20 | 100%
Sprint 3 | Week 7–8 | 22 | 22 | 22 | 100%
Sprint 4 | Week 9 | 25 | 25 | 25 | 100%
Sprint 5 | Week 10 | 24 | 24 | 24 | 100%
Sprint 6 | Week 11–12 | 26 | 26 | 26 | 100%

## Velocity Trend
Velocity Trend Chart
Sprint | Velocity
Sprint 1 | 18
Sprint 2 | 20
Sprint 3 | 22
Sprint 4 | 25
Sprint 5 | 24
Sprint 6 | 26

## Velocity Trend Analysis
Sprint-to-Sprint Improvement
Sprint Comparison | Previous Velocity | Current Velocity | Difference
Sprint 1 → Sprint 2 | 18 | 20 | 2
Sprint 2 → Sprint 3 | 20 | 22 | 2
Sprint 3 → Sprint 4 | 22 | 25 | 3
Sprint 4 → Sprint 5 | 25 | 24 | -1
Sprint 5 → Sprint 6 | 24 | 26 | 2

## KPI Summary
KPI | Target | Actual
Average Velocity | 20 | 22.5
Final Velocity | 24+ | 26
Sprint Completion Rate | 90% | 100%
Sprint Delivery Success | 90% | 100%